## Calendar external
Week number | Start Date | End Date | Activity type | Activities | Comments
37 | 2025-09-08 | 2025-09-11 | Schedule | T2 Synchronised Standard day
37 | 2025-09-10 | 2025-09-10 | Special testing | Open ECONSII from 10:00 - 12:00 CET
37 | 2025-09-10 | 2025-09-10 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
37 | 2025-09-11 | 2025-09-11 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
37 | 2025-09-12 | 2025-09-12 | Schedule | T2 Synchronised Release day
38 | 2025-09-15 | 2025-09-15 | Reporting | Service Transition Status Report (STSR) for T2 R2025.NOV in Pre-Production (cut-off and delivery to T2-WG)
38 | 2025-09-15 | 2025-09-18 | Schedule | T2 Synchronised Standard day
38 | 2025-09-16 | 2025-09-25 | Release testing | Reduction of warehoused payment period parameter in view of T2 R2025.NOV deployment | Parameter value “9” will be effective for warehoused payments instructed on 16/09/2025. Afterwards, the value is reduced on a daily basis until “0” becomes effective for 25/09/2025, i.e. no warehoused payments can then be done in UTEST until the new T2 R2025.NOV software is installed
38 | 2025-09-17 | 2025-09-17 | Reporting | T2-WG Go / No-go decision to deploy T2 R2025.NOV to Pre-Production | 8 business days before UTEST deployment
38 | 2025-09-17 | 2025-09-17 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
38 | 2025-09-17 | 2025-09-17 | Special testing | Open ECONSII from 10:00 - 12:00 CET
38 | 2025-09-18 | 2025-09-18 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
38 | 2025-09-19 | 2025-09-19 | Schedule | T2 Synchronised Release day
39 | 2025-09-22 | 2025-09-24 | Schedule | T2 Synchronised Standard day
39 | 2025-09-23 | 2025-09-24 | ORT | T2 ORT "ECONS II two-day test involving T2S and ECMS"
39 | 2025-09-23 | 2025-09-24 | Special testing | Open ECONSII (exact timings to be confirmed in line with ORT script)
39 | 2025-09-24 | 2025-09-24 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
39 | 2025-09-25 | 2025-09-25 | Schedule | T2 Synchronised Release day | to facilitate deployment of R2025.NOV
39 | 2025-09-25 | 2025-09-25 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
39 | 2025-09-26 | 2025-09-26 | Schedule | T2 closing day | to facilitate deployment of R2025.NOV
39 | 2025-09-26 | 2025-09-26 | Release deployment | T2 R2025.NOV deployment to Pre-Production (Packages 1-6) | Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
40 | 2025-09-29 | 2025-09-29 | Schedule | T2 Synchronised Standard day
40 | 2025-09-29 | 2025-09-29 | Release testing | Start of testing of T2 R2025.NOV scope elements in Pre-Production
40 | 2025-09-29 | 2025-10-03 | Release testing | T2 R2025.NOV - CB regression testing - 1st window
40 | 2025-09-29 | 2025-10-03 | Release testing | Testing of CR-139 in T2 R2025.NOV - Parameter for pagination of camt.053 reduced to 100
40 | 2025-09-29 | 2025-10-03 | Release testing | T2 R2025.NOV release testing in Pre-Production
40 | 2025-09-30 | 2025-09-30 | Schedule | T2 Synchronised Standard day - RSOD event delayed | To support the testing of PBI235189 as part of T2 R2025.NOV the RSOD event will be delayed by about 15 minutes and released once event CRTI started. No impact on event RRTI is expected.
40 | 2025-10-01 | 2025-10-01 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
40 | 2025-10-01 | 2025-10-01 | Special testing | Open ECONSII from 10:00 - 14:00 CET | extended slot to support PTCB ECONSII regular testing
40 | 2025-10-01 | 2025-10-02 | Schedule | T2 Synchronised Standard day
40 | 2025-10-02 | 2025-10-02 | Release deployment | T2 R2025.NOV deployment (Package 7) | RDs only / Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
40 | 2025-10-02 | 2025-10-02 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
40 | 2025-10-03 | 2025-10-03 | Special testing | BILL invoice for NCBs | Billing period 01/09/-30/09/2025
40 | 2025-10-03 | 2025-10-03 | Schedule | T2 Synchronised Release day
41 | 2025-10-06 | 2025-10-07 | Release testing | Testing of CR-155 in T2 R2025.NOV – No AML to be triggered in UTEST for any participant/community | All relevant cash accounts for all participants in UTEST must be configured to have a positive aggregated balance at EoD and have their credit line unused. (Note: the aggregated balance is considered when triggering the T2 AML, i.e. the aggregate of all balances of all TARGET Services [including T2S and TIPS])
41 | 2025-10-06 | 2025-10-08 | Release testing | T2 R2025.NOV - CB regression testing - 1st window
41 | 2025-10-06 | 2025-10-09 | Schedule | T2 Synchronised Standard day
41 | 2025-10-06 | 2025-10-10 | Release testing | Testing of CR-139 in T2 R2025.NOV - Parameter for pagination of camt.053 reduced to 100
41 | 2025-10-06 | 2025-10-10 | Release testing | T2 R2025.NOV release testing in Pre-Production
41 | 2025-10-08 | 2025-10-08 | Special testing | Open ECONSII from 10:00 - 12:00 CET
41 | 2025-10-08 | 2025-10-08 | ORT | T2S ORT "Delay in RTGS start (processing without liquidity) (DKK)" with impact on T2 | Impact on T2: a delay in the start of new business day in CLM and RTGS will be simulated
41 | 2025-10-08 | 2025-10-08 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
41 | 2025-10-09 | 2025-10-09 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
41 | 2025-10-10 | 2025-10-10 | Release deployment | T2 R2025.NOV deployment (Package 8) | RDs only / Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
41 | 2025-10-10 | 2025-10-10 | Schedule | T2 Synchronised Release day
42 | 2025-10-13 | 2025-10-14 | Release testing | Testing of CR-155 in T2 R2025.NOV – No AML to be triggered in UTEST for any participant/community | All relevant cash accounts for all participants in UTEST must be configured to have a positive aggregated balance at EoD and have their credit line unused. (Note: the aggregated balance is considered when triggering the T2 AML, i.e. the aggregate of all balances of all TARGET Services [including T2S and TIPS])
42 | 2025-10-13 | 2025-10-16 | Schedule | T2 Synchronised Standard day
42 | 2025-10-13 | 2025-10-17 | Release testing | T2 R2025.NOV release testing in Pre-Production
42 | 2025-10-13 | 2025-10-17 | Release testing | Testing of CR-139 in T2 R2025.NOV - Parameter for pagination of camt.053 reduced to 100
42 | 2025-10-15 | 2025-10-15 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
42 | 2025-10-15 | 2025-10-15 | Special testing | Open ECONSII from 10:00 - 12:00 CET
42 | 2025-10-16 | 2025-10-16 | ORT | T2 ORT "Suspension of a participant"
42 | 2025-10-16 | 2025-10-16 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
42 | 2025-10-17 | 2025-10-17 | Release deployment | T2 R2025.NOV deployment (Package 9) | critical RDs only / Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
42 | 2025-10-17 | 2025-10-17 | Schedule | T2 Synchronised Release day
43 | 2025-10-20 | 2025-10-23 | Schedule | T2 Live Timing | to support UT campaign for T2 & ECMS R2025.NOV
43 | 2025-10-20 | 2025-10-24 | Release testing | T2 R2025.NOV release testing in Pre-Production
43 | 2025-10-22 | 2025-10-22 | Special testing | Open ECONSII from 10:00 - 12:00 CET
43 | 2025-10-22 | 2025-10-22 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
43 | 2025-10-23 | 2025-10-23 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
43 | 2025-10-24 | 2025-10-24 | Release deployment | T2 R2025.NOV deployment (Package 10) | critical RDs only / Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
43 | 2025-10-24 | 2025-10-24 | Schedule | T2 Synchronised Release day
44 | 2025-10-27 | 2025-10-30 | Schedule | T2 Live Timing | to support UT campaign for T2 & ECMS R2025.NOV
44 | 2025-10-27 | 2025-10-31 | Release testing | T2 R2025.NOV release testing in Pre-Production
44 | 2025-10-27 | 2025-10-31 | Release testing | T2 R2025.NOV - CB regression testing - 2nd window
44 | 2025-10-29 | 2025-10-29 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
44 | 2025-10-29 | 2025-10-29 | Special testing | Open ECONSII from 10:00 - 12:00 CET
44 | 2025-10-30 | 2025-10-30 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
44 | 2025-10-31 | 2025-10-31 | Release deployment | T2 R2025.NOV deployment (Package 11) | critical RDs only / Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
44 | 2025-10-31 | 2025-10-31 | Schedule | T2 Synchronised Release day
45 | 2025-11-03 | 2025-11-05 | Release testing | T2 R2025.NOV release testing in Pre-Production
45 | 2025-11-03 | 2025-11-06 | Schedule | T2 Synchronised Standard day
45 | 2025-11-05 | 2025-11-05 | Special testing | BILL invoice for NCBs | Billing period 01/10/-31/10/2025
45 | 2025-11-05 | 2025-11-05 | Special testing | Open ECONSII from 10:00 - 12:00 CET
45 | 2025-11-05 | 2025-11-05 | Release testing | End of testing of T2 R2025.NOV scope elements in Pre-Production
45 | 2025-11-05 | 2025-11-05 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
45 | 2025-11-06 | 2025-11-06 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
45 | 2025-11-07 | 2025-11-07 | Release deployment | T2 R2025.NOV deployment (Package 12) | critical RDs only / Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
45 | 2025-11-07 | 2025-11-07 | Schedule | T2 Synchronised Release day
46 | 2025-11-10 | 2025-11-12 | Schedule | T2 Synchronised Standard day
46 | 2025-11-12 | 2025-11-12 | Special testing | Open ECONSII from 09:00 - 14:00 CET | to support DECB & FRCB ECONSII regular testing
46 | 2025-11-12 | 2025-11-12 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
46 | 2025-11-13 | 2025-11-13 | Schedule | T2 Live Timing | To support FRCB testing activities for T2 community
46 | 2025-11-13 | 2025-11-13 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
46 | 2025-11-14 | 2025-11-14 | Schedule | T2 Synchronised Release day
47 | 2025-11-17 | 2025-11-20 | Schedule | T2 Synchronised Standard day
47 | 2025-11-19 | 2025-11-19 | Special testing | Open ECONSII from 10:00 - 12:00 CET
47 | 2025-11-19 | 2025-11-19 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
47 | 2025-11-20 | 2025-11-20 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
47 | 2025-11-21 | 2025-11-21 | Schedule | T2 Synchronised Release day
48 | 2025-11-24 | 2025-11-27 | Schedule | T2 Synchronised Standard day
48 | 2025-11-26 | 2025-11-26 | Special testing | Open ECONSII from 10:00 - 12:00 CET
48 | 2025-11-26 | 2025-11-26 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
48 | 2025-11-27 | 2025-11-27 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
48 | 2025-11-28 | 2025-11-28 | Schedule | T2 Synchronised Release day
49 | 2025-12-01 | 2025-12-04 | Schedule | T2 Synchronised Standard day
49 | 2025-12-03 | 2025-12-03 | Special testing | BILL invoice for NCBs | Billing period 01/11/-30/11/2025
49 | 2025-12-03 | 2025-12-03 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
49 | 2025-12-03 | 2025-12-03 | Special testing | Open ECONSII from 10:00 - 12:00 CET
49 | 2025-12-04 | 2025-12-04 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
49 | 2025-12-05 | 2025-12-05 | Schedule | T2 Synchronised Release day
50 | 2025-12-08 | 2025-12-11 | Schedule | T2 Synchronised Standard day
50 | 2025-12-10 | 2025-12-10 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
50 | 2025-12-10 | 2025-12-10 | ORT | T2S ORT "RAD Tests (Inter regional failover with loss of data)" with impact on T2 | Impact on T2: a snapshot of the system will be taken during the evening before the test and reloaded the day after in the morning. All the updates performed in the system (UTEST), included CoCo, will be lost.
50 | 2025-12-10 | 2025-12-10 | Special testing | Open ECONSII from 10:00 - 12:00 CET
50 | 2025-12-11 | 2025-12-11 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
50 | 2025-12-12 | 2025-12-12 | Schedule | T2 Synchronised Release day
51 | 2025-12-15 | 2025-12-18 | Schedule | T2 Synchronised Standard day
51 | 2025-12-17 | 2025-12-17 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
51 | 2025-12-17 | 2025-12-17 | Special testing | Open ECONSII from 10:00 - 12:00 CET
51 | 2025-12-18 | 2025-12-18 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
51 | 2025-12-19 | 2025-12-19 | Schedule | T2 Synchronised Release day
52 | 2025-12-22 | 2025-12-23 | Schedule | T2 Synchronised Standard day
52 | 2025-12-24 | 2025-12-24 | Schedule | T2 closing day | Christmas Eve
52 | 2025-12-25 | 2025-12-25 | Schedule | T2 closing day | Christmas Day
52 | 2025-12-26 | 2025-12-26 | Schedule | T2 closing day | Boxing Day
1 | 2025-12-29 | 2025-12-30 | Schedule | T2 Synchronised Standard day
53 | 2025-12-30 | 2025-12-30 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
1 | 2025-12-31 | 2025-12-31 | Schedule | T2 closing day | New Year's Eve
1 | 2026-01-01 | 2026-01-01 | Schedule | T2 Synchronised Standard day
1 | 2026-01-02 | 2026-01-02 | Schedule | T2 Synchronised Release day
2 | 2026-01-06 | 2026-01-06 | Special testing | BILL invoice for NCBs | Billing period 01/12/-31/12/2025
11 | 2026-03-12 | 2026-03-12 | Reporting | Service Transition Status Report (STSR) for T2 R2026.JUN in Pre-Production (cut-off and delivery T2-WG)
11 | 2026-03-13 | 2026-03-13 | Reporting | T2-WG Go / No-go decision to deploy T2 R2026.JUN to Pre-Production | 8 business days before UTEST deployment
13 | 2026-03-27 | 2026-03-27 | Release deployment | T2 R2026.JUN deployment to Pre-Production (Packages 1-8) | Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
14 | 2026-03-30 | 2026-03-30 | Release testing | Start of testing of T2 R2026.JUN scope elements in Pre-Production
14 | 2026-03-30 | 2026-04-03 | Release testing | T2 R2026.JUN release testing in Pre-Production
15 | 2026-04-06 | 2026-04-10 | Release testing | T2 R2026.JUN release testing in Pre-Production
16 | 2026-04-13 | 2026-04-17 | Release testing | T2 R2026.JUN release testing in Pre-Production
16 | 2026-04-17 | 2026-04-17 | Release deployment | T2 R2026.JUN deployment (Package 9) | RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
17 | 2026-04-20 | 2026-04-24 | Release testing | T2 R2026.JUN release testing in Pre-Production
17 | 2026-04-24 | 2026-04-24 | Release deployment | T2 R2026.JUN deployment (Package 10) | RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
18 | 2026-04-27 | 2026-05-01 | Release testing | T2 R2026.JUN release testing in Pre-Production
18 | 2026-04-30 | 2026-04-30 | Release deployment | T2 R2026.JUN deployment (Package 11) | RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
19 | 2026-05-04 | 2026-05-08 | Release testing | T2 R2026.JUN release testing in Pre-Production
19 | 2026-05-07 | 2026-05-07 | Release deployment | T2 R2026.JUN deployment (Package 12) | RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
20 | 2026-05-11 | 2026-05-15 | Release testing | T2 R2026.JUN release testing in Pre-Production
20 | 2026-05-13 | 2026-05-13 | Release deployment | T2 R2026.JUN deployment (Package 13) | Critical RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
21 | 2026-05-18 | 2026-05-22 | Release testing | T2 R2026.JUN release testing in Pre-Production
21 | 2026-05-22 | 2026-05-22 | Release deployment | T2 R2026.JUN deployment (Package 14) | Critical RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
22 | 2026-05-25 | 2026-05-27 | Release testing | T2 R2026.JUN release testing in Pre-Production
22 | 2026-05-27 | 2026-05-27 | Release testing | End of testing of T2 R2026.JUN scope elements in Pre-Production
22 | 2026-05-29 | 2026-05-29 | Release deployment | T2 R2026.JUN deployment (Package 15) | Critical RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
23 | 2026-06-05 | 2026-06-05 | Release deployment | T2 R2026.JUN deployment (Package 16) | Critical RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
38 | 2026-09-15 | 2026-09-15 | Reporting | T2-WG Go / No-go decision to deploy T2 R2026.NOV to Pre-Production
39 | 2026-09-25 | 2026-09-25 | Release deployment | T2 R2026.NOV deployment to Pre-Production (Packages 1-6)
40 | 2026-10-02 | 2026-10-02 | Release deployment | T2 R2026.NOV deployment (Package 7) | RD only
41 | 2026-10-09 | 2026-10-09 | Release deployment | T2 R2026.NOV deployment (Package 8) | RD only
42 | 2026-10-16 | 2026-10-16 | Release deployment | T2 R2026.NOV deployment (Package 9) | critical RD only
43 | 2026-10-23 | 2026-10-23 | Release deployment | T2 R2026.NOV deployment (Package 10) | critical RD only
44 | 2026-10-30 | 2026-10-30 | Release deployment | T2 R2026.NOV deployment (Package 11) | critical RD only
45 | 2026-11-06 | 2026-11-06 | Release deployment | T2 R2026.NOV deployment (Package 12) | critical RD only